## Planing
TEST SCHEDULE
| Activities/ Tasks | Person in charge | Status | Planned Start date | Planned End date | Planned Effort (man-hours)
Initiation
Study system
| Research datasheet, PCB, SCH | BachDX, BanDX,LongNT, HaiDQ | Finished | 2014-01-23 | 2014-01-24 | 20
| Learn how to use Digital Multimeter | BachDX, BanDX,LongNT, HaiDQ | Finished | 2014-01-24 | 2014-01-25 | 20
Planning
Test Plan
| Create Schedule Test | BachDX | Finished | 2014-01-26 | 2014-01-27 | 8
Design
Create Testcase
| Before Solder | BachDX | Finished | 2014-02-13 | 2014-02-13 | 4
| After Solder | BachDX | Finished | 2014-02-14 | 2014-02-15 | 8
| After Programing | BachDX | Finished | 2014-02-15 | 2014-02-16 | 8
Execute Manual Test
Dual colors led v1.0
| Before Solder | BachDX | Finished | 2014-01-20 | 2014-01-20 | 4
| After Solder | TungNT | Finished | 2014-02-25 | 2014-02-26 | 8
| After Programing | LongNT | Finished | 2014-02-27 | 2014-03-05 | 8
Triple colors led v1.0
| Before Solder | BanDV | Finished | 2014-01-20 | 2014-01-20 | 4
| After Solder | TungNT | Finished | 2014-02-25 | 2014-02-26 | 8
| After Programing | HaiDQ | Finished | 2014-02-27 | 2014-03-05 | 8
Triple colors led v2.0
| Before Solder | BachDX | Finished | 2014-03-05 | 2014-03-05 | 4
| After Solder | BachDX | Finished | 2014-03-10 | 2014-03-10 | 8
| After Programing | LongNT | Finished | 2014-03-15 | 2014-03-25 | 8
Test Report
Dual colors led v1.0
| Create Test Report | BachDX | Finished | 2014-04-05 | 2014-04-05 | 4
Triple colors led v1.0
| Create Test Report | BachDX | Finished | 2014-04-06 | 2014-04-06 | 4
Triple colors led v2.0
| Create Test Report | BachDX | Finished | 2014-04-07 | 2014-04-07 | 4
[5 empty] | Total | 140

## Tool and Enviroment
TEST ENVIRONMENT
Type | Purpose | Owner
Personal Computer | See PCB,SCH, Design | Tester
Digital Multimeter DT9205 A+ | Check communication circuit correct with circuit principle | Tester
Digital Multimeter VC9803A+ | Check communication circuit correct with circuit principle | Tester
Pickit 2 | Download programing | Tester
Supply power 12V-1A | Supply power | Tester
Supply power 5V-1A | Supply power | Tester
Supply power 12V-2A | Supply power | Tester